## Sheet1
Location | Major Category | Scope/Description | Construction Project Coordinator | Project Advisor | Discipline Lead | Office Manager | Principal | School Ext. | Bond Sign? | Summer 2019 Work | Scheduled Action Year 2019 | Scheduled Action Year 2020 | Scheduled Action Year 2021 | Scheduled Action Year 2022 | Recommended Budget as of January 2019 | Code | Project Implementation Notes
Cache La Poudre MS | Life Safety Security | Horns and strobe installation | Gustafson | Little | TLH Fire |  |  |  |  | No | Design | Construction |  |  | 80000 | 4-230-57-PP02
Fort Collins HS | Life Safety Security | Horns and strobe installation | Gustafson | Schlicting | TLH Fire |  |  |  |  | No | Design | Construction |  |  | 145000 | 4-340-57-PP03
Lesher MS | Life Safety Security | Fire alarm system replacement | Lee | Schlicting | TLH Fire | Jeannie Mitchell | Tom Dodd | 3803 | No | No | Design | Construction |  |  | 183000 | 4-240-57-PP02
Lincoln MS | Life Safety Security | Horns and strobe installation | Gustafson | Little | TLH Fire |  |  |  |  | No |  |  | Design | Construction | 83000 | 4-250-57-PP02
Poudre HS | Life Safety Security | Horns and strobe installation | Gustafson | Schlicting | TLH Fire |  |  |  |  | No |  | Design | Construction |  | 145000 | 4-350-57-PP03
Rocky Mountain HS | Life Safety Security | Horns and strobe installation | Lee | Schlicting | TLH Fire |  |  |  |  | No | Design | Construction |  |  | 145000 | 4-360-57-PP02
Traut ES | Life Safety Security | Horns and strobe installation | Lee | Schlicting | TLH Fire |  |  |  |  | No | Design | Construction |  |  | 50000 | 4-188-56-PP01
Webber MS | Life Safety Security | Horns and strobe installation | Gustafson | Little | TLH Fire |  |  |  |  | No | Design | Construction |  |  | 81000 | 4-270-57-PP04
Werner ES | Life Safety Security | Fire alarm system replacement | Lee | Schlicting | TLH Fire |  |  |  |  | No | Design | Construction |  |  | 55000 | 4-190-57-PP03
Zach ES Total | [14 empty] | 0
Grand Total | [14 empty] | 967000